## Sheet1
PROJECT DEVELOPMENT AND COMPLETION TRACKER
Project ID: Version 1.2 (Flutter)
Project Start Date: 15-09-2023
Project End Date: 31-10-2023
Project Description: Andriod application for kids to learn about online community.
| Name of Team Member | Role
Project Architech | Eya Tomar | Arch.
Team Member
Project Development | Vedant Mhaske | Front End
Team Members | Suraj Kolpe | Back End
| Ankit Bharadwaj | Back End
Sprint no. | Task Name | Sub Task | Task Status | Assigned To | Completion Status
1 | User Interface | Design the app's user interface with a kid-friendly and engaging look. | Complete |  | 100%
|  | Create visuals that appeal to children. | Complete
|  | Design layout and navigation for easy access to activities. | Complete
2 | User Registration and Login | Implement a user registration and login system with parental controls. | Complete
|  | Create child profiles for a personalized experience. | Complete
3 | Homepage | Design the homepage with attractive banners and featured activities. | Complete
|  | Display recent and popular activities | On hold
4 | Activity Modules | Create interactive modules for teaching online behavior. | Complete
|  | Include videos, quizzes, games, and workshops. | Complete
|  | Develop a user-friendly interface for each activity. | In Progress
|  | Implement a progress tracker to monitor a child's learning. | On hold
5 | Role-Play Activities | Design and develop interactive role-play scenarios. | Complete
|  | Enable children to make decisions and learn from the consequences. | Complete
|  | Include character customization options. | Complete
6 | Videos | Implement a video player with age-appropriate content. | Complete
|  | Allow for video bookmarking and offline viewing. | Complete
7 | User Engagement | Include features like badges and rewards to motivate kids. | Complete
|  | Create a feedback system for children to express their thoughts | In Progress
8 | Parental Dashboard | Develop a separate dashboard for parents. | On hold
|  | Provide insights into their child's progress and usage. | On hold
|  | Include tools for setting content restrictions and monitoring. | Complete
9 | Notifications | Set up push notifications for new activities, progress updates, and important messages. | Complete
|  | Ensure notification preferences are customizable for parents. | Complete
10 | Usability | Ensure a straightforward and intuitive user experience. | Complete
11 | Database Design | Create a database schema to store user profiles, progress data, and activity information.
12 | User Authentication and Authorization: | Set up user authentication using secure protocols
13 | Content Management | Establish a system for content management and updates
14 | Progress Tracking | Develop a system for tracking and storing a child's progress in activities.
Enable data synchronization across devices.
15 | Video Streaming | Integrate video streaming services
Implement features like video recommendations and parental controls.
16 | Notifications | Set up a notification service to send push notifications to users.
Create templates for various notification types.
17 | Analytics and Reporting | Implement analytics tools to track app usage and user behavior.
Generate reports for both parents and administrators.
18 | Security | Implement robust security measures to protect user data and ensure safe online usage for children.
Regularly audit and update security practices.
19 | Server Infrastructure | Choose a scalable server infrastructure to handle increasing user loads.
Ensure high availability and uptime.
20 | APIs | Develop APIs to connect the app with external services and data sources.
Secure API endpoints and manage data transfers.